## Playbook
Project Name: | Deep learning based recommendation system
Document Date: | 2021-12-01
General Description: | In this project team X will develop recommendation system for Y vertical to improve current rule-based approach.
Technologies: | Python, Spark, Tensorflow, Sagemaker
Implementation level: | Simple / Medium / Hard
Key Goal: | Increase CTR by 5% comparing to rule-based approach.
Evaluation metrics: | 1) CTR
2) needs to be able toserve at least X users per Y time
3) cost constraint during development ($X)
4) cost constraint during production ($X)
Key Features: | Features that team needs to deliver to succesfuly finish the project
Additional Features: | Features that might expand project scope and deliver additional value but are not crucial to succesfuly finish the project
Stakeholders: | Responsibilities: | [7 empty] | Approved by stakeholder:
Sponsor | list key responsibilities here, and define form of communication / reporting | [7 empty] | yes/no (adjust until all stakeholders are aligned)
Project Manager (PM) | … | [7 empty] | …
Technical Product Manager (TPM) | … | [7 empty] | …
Project Team / or specific project team groups | … | [7 empty] | …
Internal teams / stakholders | … | [7 empty] | …
ID | Task Name | Optimisitc Estimate (O) [days] | Most Likely Estimate (M) [days] | Pessimistic Estimate (P) [days] | Support Type Activities / LOE Estimate [days] | Task Predecessors | Head Count | Team | Start-Date | End-Date | Risk | Resource Cost | Resource cost estimation method | M + LOE
1 | Project Start | 1 | 1 | 1 | 0 | 0 | 3 | BookDL | 2021-12-12 | 2021-12-13 | Low | 0 | A | 1
2 | Initial Analysis | 5 | 7 | 9 | 3 | 1 | 3 | BookDL | 2021-12-13 | 2021-12-23 | Low | 900 | A | 10
3 | Feature Engineering | 6 | 8 | 10 | 3 | 2 | 3 | BookDL | 2021-12-23 | 2022-01-03 | Low | 990 | A | 11
4 | Creation of train, cross-validation, test sets | 3 | 4 | 5 | 1 | 3 | 1 | BookDL | 2022-01-03 | 2022-01-08 | Low | 150 | A | 5
5 | Model training / PoC | 7 | 9 | 11 | 4 | 4 | 3 | BookDL | 2022-01-08 | 2022-01-21 | Low | 1170 | A | 13
6 | Model evaluation, Model understanding | 3 | 4 | 5 | 1 | 5 | 1 | BookDL | 2022-01-21 | 2022-01-26 | Medium | 150 | A | 5
7 | Hyper-parameter tuning | 6 | 7 | 10 | 2 | 5 | 2 | BookDL | 2022-01-21 | 2022-01-30 | Medium | 2700 | B | 9
8 | Creation of final MVP or service | 4 | 6 | 8 | 2 | 7 | 3 | BookDL | 2022-01-30 | 2022-02-07 | Medium | 720 | A | 8
9 | Adjustments to existing environments, automation, data pipeline improvements | 6 | 8 | 9 | 3 | 8 | 3 | BookDL | 2022-02-07 | 2022-02-18 | High | 990 | A | 11
10 | Model inprovements / re-training / model optimization (i.e. pruning, quantization) | 3 | 4 | 5 | 2 | 8 | 1 | BookDL | 2022-02-07 | 2022-02-13 | Medium | 180 | A | 6
11 | Inference tests, test in staging environment | 5 | 6 | 7 | 2 | 10 | 3 | BookDL | 2022-02-13 | 2022-02-21 | Low | 720 | A | 8
12 | Creation of production ready product or service | 1 | 2 | 3 | 1 | 11 | 1 | BookDL | 2022-02-21 | 2022-02-24 | Medium | 90 | A | 3
13 | Seting up maintenance services, model understading and controling in production environment | 1 | 2 | 3 | 1 | 11 | 1 | BookDL | 2022-02-21 | 2022-02-24 | Low | 90 | A | 3
14 | Project Clouser | 1 | 1 | 1 | 1 | 13 | 3 | BookDL | 2022-02-24 | 2022-02-26 | Low | 180 | A | 2
[11 empty] | Total | 9030
| Total | 52 | 69 | 87 | 26 |  |  |  | A | ( M estimate + LOE ) * Head Count * ~6h/day * $5 (~cost of one mp24.xlarge or p2.8xlarge)
[9 empty] | B | ( M estimate + LOE ) * Head Count * ~6h/day * $25 (~cost of one p3.16xlarge)
|  |  |  | 78 | 3.9
|  |  |  | 95 | 4.75
|  |  |  | 113 | 5.65
[8 empty] | P | 44542 | (first date in number format for axis formatting)
Formulas:
Approved by stakeholder: = [End-Date, row above]
End-Date = [Approved by stakeholder:]+[Most Likely Estimate (M) [days]]+F27